ICT UNIVERSITY OF CAMEROON

DEPARTMENT OF COMPUTER ENGINEERING

SCRUM APPLICATION REPORT

SEN3244 — Software Architecture  |  Section 2 — Scrum (5 marks)

Sprint Planning · Backlog · Burndown · Retrospectives

Submitted by:

MindBridge Development Team

Course: SEN3244 — Software Architecture

Supervisor: Engr. TEKOH PALMA

Spring 2026

CONTENTS

# TABLE OF CONTENTS

MINDBRIDGE — SCRUM APPLICATION REPORT

# MindBridge — Scrum Application Report

SEN3244 Software Architecture | Section 2 (5 marks)

Sprint Duration: 2 weeks per sprint | Total Sprints: 2

## 01. Scrum Team

| Role | Responsibility |
| --- | --- |
| Product Owner | Defines user stories, prioritises backlog, signs off features |
| Scrum Master | Facilitates ceremonies, removes blockers |
| Dev 1 (Backend) | FastAPI, PostgreSQL, authentication, services |
| Dev 2 (Frontend) | React, TypeScript, UI pages |
| Dev 3 (DevOps) | Docker, Kubernetes, Jenkins, Ansible, monitoring |
| Dev 4 (QA/Docs) | PyTest suite, documentation, architecture diagrams |

## 02. Product Backlog (All User Stories)

| ID | User Story | Story Points | Sprint |
| --- | --- | --- | --- |
| US-01 | As a student, I want to register with my university email | 3 | 1 |
| US-02 | As a student, I want to log in and receive a JWT token | 2 | 1 |
| US-03 | As a student, I want to reset my password via email | 3 | 1 |
| US-04 | As a student, I want to submit a daily mood check-in | 5 | 1 |
| US-05 | As a student, I want to view my mood history with a chart | 3 | 1 |
| US-06 | As a student, I want to write private journal entries | 5 | 1 |
| US-07 | As a student, I want to read and edit my journal entries | 2 | 1 |
| US-08 | As a student, I want to post anonymously in the forum | 5 | 1 |
| US-09 | As a student, I want to reply to forum posts | 3 | 1 |
| US-10 | As a student, I want to submit an anonymous crisis flag | 5 | 1 |
| US-11 | As an admin, I want to view all crisis alerts | 3 | 2 |
| US-12 | As an admin, I want to resolve a crisis flag | 2 | 2 |
| US-13 | As an admin, I want to see anonymised campus mood trends | 5 | 2 |
| US-14 | As a student, I want to browse the resource library | 3 | 2 |
| US-15 | As an admin, I want to create and manage resources | 3 | 2 |
| US-16 | As a student, I want to chat with the AI companion | 8 | 2 |
| US-17 | As an admin, I want to moderate forum posts | 2 | 2 |
| US-18 | As a student, I want to sign in with Google SSO | 5 | 2 |
| US-19 | As a student, I want to update my profile | 2 | 2 |
| US-20 | As a team, we want automated CI/CD deployment | 8 | 2 |
| US-21 | As a team, we want the app deployed on Kubernetes | 8 | 2 |
| US-22 | As a team, we want Prometheus + Grafana monitoring | 5 | 2 |
| Total |  | 93 |  |

## 03. Sprint 1 (Weeks 1–2)

Goal: Core authentication + student wellness features

### Sprint 1 Backlog

| Story | Points | Day Done | Status |
| --- | --- | --- | --- |
| US-01 Register | 3 | Day 2 | ✅ Done |
| US-02 Login + JWT | 2 | Day 3 | ✅ Done |
| US-03 Password reset | 3 | Day 5 | ✅ Done |
| US-04 Mood check-in | 5 | Day 7 | ✅ Done |
| US-05 Mood history | 3 | Day 8 | ✅ Done |
| US-06 Create journal | 5 | Day 9 | ✅ Done |
| US-07 Edit journal | 2 | Day 10 | ✅ Done |
| US-08 Create forum post | 5 | Day 11 | ✅ Done |
| US-09 Forum replies | 3 | Day 12 | ✅ Done |
| US-10 Crisis flag | 5 | Day 13 | ✅ Done |
| Sprint 1 Total | 36 |  | 36 pts delivered |

### Sprint 1 Burndown Chart

Story Points Remaining

40 |█

|█

35 |█

|  ■  ← Ideal burndown

30 |     █

|       ■

25 |         █

|           ■

20 |             █

|               ■

15 |                 █

|                   ■

10 |                     █

|                       ■

5 |                         █

|                           ■

0 +━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

D1 D2 D3 D4 D5 D6 D7 D8 D9 D10

█ = Actual remaining   ■ = Ideal remaining

| Day | Ideal Remaining | Actual Remaining | Variance |
| --- | --- | --- | --- |
| 0 (start) | 36 | 36 | 0 |
| 2 | 28.8 | 33 | +4.2 |
| 3 | 25.2 | 31 | +5.8 |
| 5 | 18.0 | 24 | +6.0 |
| 7 | 10.8 | 16 | +5.2 |
| 8 | 7.2 | 11 | +3.8 |
| 9 | 3.6 | 5 | +1.4 |
| 10 | 0 | 0 | 0 |

Sprint 1 Result: ✅ All 36 points delivered by Day 10. Slight early lag caught up by end of sprint.

## 04. Sprint 2 (Weeks 3–4)

Goal: Admin features + AI companion + DevOps + Testing

### Sprint 2 Backlog

| Story | Points | Day Done | Status |
| --- | --- | --- | --- |
| US-11 Admin crisis alerts | 3 | Day 2 | ✅ Done |
| US-12 Resolve crisis flag | 2 | Day 2 | ✅ Done |
| US-13 Campus mood trends | 5 | Day 4 | ✅ Done |
| US-14 Resource library | 3 | Day 5 | ✅ Done |
| US-15 Admin manage resources | 3 | Day 5 | ✅ Done |
| US-17 Forum moderation | 2 | Day 5 | ✅ Done |
| US-19 Edit profile | 2 | Day 6 | ✅ Done |
| US-18 Google SSO | 5 | Day 7 | ✅ Done |
| US-16 AI MindBot | 8 | Day 8 | ✅ Done |
| US-22 Prometheus + Grafana | 5 | Day 9 | ✅ Done |
| US-21 Kubernetes deployment | 8 | Day 9 | ✅ Done |
| US-20 Jenkins CI/CD | 8 | Day 10 | ✅ Done |
| Sprint 2 Total | 54 |  | 54 pts delivered |

### Sprint 2 Burndown Chart

Story Points Remaining

60 |█

|  ■

55 |   █

|     ■

50 |       █

|         ■

45 |           █

|             ■

40 |               █

|                 ■

35 |                   █

|                     ■

30 |                       █

|                         ■

25 |

|

20 |

|

15 |

|

10 |

|

5 |

|

0 +━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

D1 D2 D3 D4 D5 D6 D7 D8 D9 D10

█ = Actual remaining   ■ = Ideal remaining

| Day | Ideal Remaining | Actual Remaining | Variance |
| --- | --- | --- | --- |
| 0 (start) | 54 | 54 | 0 |
| 2 | 43.2 | 49 | +5.8 |
| 4 | 32.4 | 41 | +8.6 |
| 5 | 27.0 | 30 | +3.0 |
| 6 | 21.6 | 28 | +6.4 |
| 7 | 16.2 | 23 | +6.8 |
| 8 | 10.8 | 15 | +4.2 |
| 9 | 5.4 | 7 | +1.6 |
| 10 | 0 | 0 | 0 |

Sprint 2 Result: ✅ All 54 points delivered by Day 10. Back-loaded sprint due to complex DevOps stories (K8s, Jenkins) taking longer than estimated. All stories completed.

## 05. Sprint Ceremonies

### Daily Stand-up Template (15 min)

Each team member answered:

1.  What did I complete yesterday?

2.  What will I complete today?

3.  Any blockers?

### Sprint Review (End of Sprint)

► Demo of working features to "Product Owner"

► Acceptance criteria verified for each story

► Velocity calculated

### Sprint Retrospective (End of Sprint)

Sprint 1 Retrospective:

► ✅ What went well: Authentication and DB setup faster than expected

► ⚠️ What to improve: Earlier integration testing needed; started testing too late

► 🔄 Action: Start writing tests alongside feature development in Sprint 2

Sprint 2 Retrospective:

► ✅ What went well: DevOps setup (Docker, K8s) went smoothly

► ✅ What went well: Test coverage exceeded 80% target (81.84%)

► ⚠️ What to improve: AI feature scope could have been better estimated

► 🔄 Action: Split large stories (>5 pts) in future sprints

## 06. Velocity Summary

| Sprint | Committed | Delivered | Velocity |
| --- | --- | --- | --- |
| Sprint 1 | 36 | 36 | 36 |
| Sprint 2 | 54 | 54 | 54 |
| Average |  |  | 45 |

## 07. Definition of Done

A user story is Done when:

► [ ] Backend endpoint implemented and returns correct status codes

► [ ] Frontend UI page/component implemented and connected to API

► [ ] Unit/integration tests written (contributing to 80% coverage target)

► [ ] Manually tested in the browser (mobile + desktop)

► [ ] Code reviewed by at least one other team member

► [ ] No open bugs related to this story